## Sheet1
NO. | Category | Work Product | Unit | Quality |  | 22/05/2012 |  |  |  | 24/05/2012 |  |  |  | 29/05/2012 |  |  |  | 31/05/2012 |  |  |  | 2012-03-06 |  |  |  | 2012-05-06 |  |  |  | 2012-07-06
|  |  |  | Seft review | Peer review | A | B | C | D | A | B | C | D | A | B | C | D | A | B | C | D | A | B | C | D | A | B | C | D | A | B | C | D
1 | report1
2 | report2 | Software Project Management Plan
3 |  | Problem Definition | Page | 3/18 | 0/15 | 24/05/2012 A: 3; 24/05/2012 B: 3; 24/05/2012 C: 3; 24/05/2012 D: 3
4 |  | Project Management Plan | Page | 4/18 | 0/14 | 24/05/2012 A: 3; 24/05/2012 B: 3; 24/05/2012 C: 3; 24/05/2012 D: 3
5 |  | Project Organization | Page | 5/18 | 0/13 | 24/05/2012 A: 3; 24/05/2012 B: 4; 24/05/2012 C: 3; 24/05/2012 D: 3
6 |  | Microsoft Project Plan | Page
7 |  | Coding Covention | Page |  |  | 24/05/2012 A: 0; 24/05/2012 B: 27; 24/05/2012 C: 27; 24/05/2012 D: 27
8 | SRS | SRS document | Page |  |  | 24/05/2012 B: 50; 24/05/2012 C: 18; 24/05/2012 D: 400; 29/05/2012 A: 79; 29/05/2012 B: 250; 29/05/2012 C: 97; 29/05/2012 D: 400; 31/05/2012 B: 300; 31/05/2012 C: 97; 31/05/2012 D: 400; 2012-03-06 B: 400; 2012-03-06 C: 97; 2012-03-06 D: 400
9 |  | HTML layout | Screen |  |  | 2012-03-06 D: 23
10 | MODULE | USE CASE | Screen
11
12 | ADMIN |  |  |  |  | 2012-03-06 D: 2
13 |  | CREATE PROJECT | Screen | bar: 2012-03-06 D
14 |  | ADD USER TO PROJECT | Screen | bar: 2012-03-06 D
15 |  | CREATE USER | Screen | bar: 2012-03-06 D
16 |  | CONFIG MODULE | Screen |  |  | 2012-03-06 D: 2
17 |  | MANAGE USER | Screen |  |  | 2012-03-06 D: 2
18 | TIMESHEET
19 |  | SEARCH | Screen
20 |  | ADD, UPDATE TS | Screen
21 |  | APPROVE, REJECT TS | Screen
|  | REPORT | Screen
|  | EXPORT | Screen
PROJECT
|  | manage info | Screen | bar: 2012-03-06 D
|  | view info | Screen | bar: 2012-03-06 D
|  | report | Screen | bar: 2012-03-06 D
|  | add user to prj | Screen | bar: 2012-03-06 D
|  | manage user | Screen | bar: 2012-03-06 D
|  | cost(budget, expense) | Screen |  |  | 2012-03-06 D: 5
|  | risk, issue, change request | Screen |  |  | 2012-03-06 D: 4
DMS
|  | search | Screen
|  | create defect | Screen
|  | update defect | Screen
|  | close defect | Screen
|  | report | Screen
|  | export to excel | Screen
DASHBOARD
|  | search | Screen
|  | export to excel | Screen
Screen
| PLANNER |  | Screen
|  | Add task | Screen
|  | update task | Screen
|  | delete task | Screen
|  | * import mpp file | Screen
|  | report | Screen
Screen
| REPORT |  | Screen
|  | report timesheet | Screen
|  | report dms | Screen
|  | report planner | Screen
|  | report project info | Screen
Screen
| REQUIREMENT |  | Screen
|  | add,update, delete requirement | Screen
|  | add use case for requirement | Screen
|  | view requirement info(tracking requirement status) | Screen
|  | export | Screen
A : On-Profress achive (weekly)
B : On-Progress plan
C: Current Archive
D:Total Plan