## OOPMS_Defects_v1.0
ID | Type | Status | Priority | Milestone | Owner | Summary | AllLabels
1 | Defect | Fixed | Low |  | truongmh60003 | [TimeSheetPortlet] Import is never used | Priority-Low, Type-Defect
2 | Defect | Accepted | Critical |  | truongmh60003 | [TimeSheetPortlet] Missing important features | Component-Logic, Priority-Critical, Type-Defect, Usability
3 | Defect | New | High |  | thachln | [TimeSheetPortlet] Not re-use the logon user of the portal | Component-Logic, Priority-High, Type-Defect
4 | Defect | Fixed | Low |  | tocongthanhhai | [ProjectEyePortlet] Java build path of project is configured not well | Priority-Low, Type-Defect
5 | Defect | New | High |  | tocongthanhhai | [ProjectEyePortlet] Done re-use DAO layer in DaoCommon | Maintainability, Priority-High, Type-Defect, Usability
6 | Defect | Fixed | Low |  | tocongthanhhai | [ProjectEyePortlet] Output file of Log4j is configured not good | Priority-Low, Type-Defect
7 | Defect | Fixed | Medium |  | tocongthanhhai | [ProjectEyePortlet] There is no use CSS of uPortal | Priority-Medium, Type-Defect
8 | Defect | Fixed | Low |  | tocongthanhhai | [ProjectEyePortlet] Could not make distribution by ANT tool | Priority-Low, Type-Defect
9 | Defect | Fixed | Medium |  | tocongthanhhai | [ProjectEyePortlet] Unnecessary folder in SVN | Priority-Medium, Type-Defect
10 | Defect | Fixed | Medium |  | tocongthanhhai | [ProjectEyePortlet] Unclear error message | Priority-Medium, Type-Defect
11 | Defect | Invalid | Medium |  | tocongthanhhai | [ProjectEyePortlet] Encapsulate properties of Project into a object | Component-Logic, Priority-Medium, Type-Defect
12 | Defect | Fixed | High |  | tocongthanhhai | [ProjectEyePortlet] No data validation and display error in Create project screen | Component-Logic, Component-UI, Priority-High, Type-Defect
13 | Defect | New | Medium |  | tocongthanhhai | [ProjectEyePortlet] Error when logon user has not existed in database | Component-Logic, Priority-Medium, Type-Defect
14 | Defect | Fixed | Low |  | giang.phamnguyen | [Planner] Could not make distribution | Priority-Low, Type-Defect
15 | Defect | Fixed | Medium |  | giang.phamnguyen | [Planner] Java build path of project is configured not well | Priority-Medium, RepeatDefect, Type-Defect
16 | Defect | Fixed | Low |  | giang.phamnguyen | [Planner] Project name/Project folder is not true | Priority-Low, Type-Defect
17 | Defect | Fixed | Medium |  | giang.phamnguyen | [Planner] Home page of the Planner Portlet is not good | Component-UI, Priority-Medium, Type-Defect
18 | Defect | Fixed | Medium |  | giang.phamnguyen | [Planner] Unclear error message | Priority-Medium, Type-Defect
19 | Defect | Fixed | Critical |  | duynd.vn | [RequirementPortlet] Add button doesnot work properly | Priority-Critical, Type-Defect
20 | Defect | Fixed | Medium |  | duynd.vn | [RequirementPortlet] Have not apply validation | Priority-Medium, Type-Defect
21 | Defect | Fixed | Medium |  | duynd.vn | [RequirementPortlet] CSS problem | Priority-Medium, Type-Defect
22 | Defect | Fixed | Low |  | duynd.vn | [RequirementPortlet] There are still test button, for test purpose | Priority-Low, Type-Defect
23 | Defect | Fixed | Medium |  | tocongthanhhai | [ProjectEyePortlet] Have not validate create project | Priority-Medium, Type-Defect
24 | Defect | Accepted | High |  | duynd.vn | [RequirementPortlet] Have not use Daocommon | Priority-High, Type-Defect
25 | Defect | Fixed | Medium |  | tocongthanhhai | [ProjectEyePortlet] Unable to update project detail | Priority-Medium, Type-Defect
26 | Defect | Fixed | High |  | duynd.vn | [RequirementPortlet] Init screen is not right | Priority-High, Type-Defect
27 | Defect | Fixed | Medium |  | giang.phamnguyen | [Planner] Do not reuse table Tasks of FMS | Component-Logic, Priority-Medium, Type-Defect
28 | Defect | New | Medium |  | giang.phamnguyen | [Planner] Do not use DaoCommon | Performance, Priority-Medium, Type-Defect
29 | Defect | Fixed | Medium |  | tocongthanhhai | [ProjectEyePortlet] Initial data for screen "Create project" is not good | Component-UI, Priority-Medium, Type-Defect
30 | Defect | Fixed | Medium |  | duynd.vn | [RequirementPortlet] Java build path of project is configured not well | Priority-Medium, Type-Defect
31 | Defect | Fixed | Low |  | duynd.vn | [RequirementPortlet] Folder 'resouce' is placed not correctly | Priority-Low, Type-Defect
32 | Defect | Fixed | Medium |  | duynd.vn | [RequirementPortlet] Error occurred but no log file | Maintainability, Priority-Medium, Type-Defect
33 | Defect | Duplicate | Medium |  | duynd.vn | [ProjectEyePortlet] Homepage is not good. | Priority-Medium, Type-Defect
34 | Defect | Fixed | Low |  | tocongthanhhai | [ProjectEyePortlet] Validation messages are not friendly | Priority-Low, Type-Defect
35 | Defect | New | Low |  | tocongthanhhai | [ProjectEyePortlet] Project detail page is not good | Priority-Low, Type-Defect
36 | Defect | Fixed | Low |  | tocongthanhhai | [ProjectEyePortlet] In screen "Create Project", Cancel button is no applied | Component-UI, Priority-Low, Type-Defect
37 | Defect | Fixed | Low |  | tocongthanhhai | [ProjectEyePortlet] In screen "Create Project", could not type the Planned End Date completely | Component-UI, Priority-Low, Re-assigned, Type-Defect
38 | Defect | Fixed | Low |  | tocongthanhhai | [ProjectEyePortlet] In screen "Create Project", no process escapse HTML character | Component-UI, Priority-Low, Security, Type-Defect
39 | Defect | New | Medium |  | tocongthanhhai | [ProjectEyePortlet] Existing projects are not displayed in the Home screen | Component-Logic, Priority-Medium, Type-Defect
40 | Defect | Fixed | Medium |  | duynd.vn | [RequirementPortlet] CSS does not fit when deploy to uPortal | Priority-Medium, Type-Defect
41 | Defect | Fixed | Low |  | truongmh60003 | [TimesheetPortlet] Not proper default date when add timesheet | Priority-Low, Type-Defect
42 | Defect | Fixed | Medium |  | truongmh60003 | [TimesheetPortlet] Unable to update Date, Project | Priority-Medium, Type-Defect
43 | Defect | Fixed | High |  | truongmh60003 | [TimesheetPortlet] Add timesheet problem - Unable to add timesheet for old date (yesterday), able to add timesheet for future (tomorrow) | Priority-High, Type-Defect
44 | Defect | Fixed | Low |  | truongmh60003 | [TimesheetPortlet] Able to update approved timesheet | Priority-Low, Type-Defect
45 | Defect | Fixed | Low |  | truongmh60003 | [TimesheetPortlet] Unable to view all timesheet of all project from search feature | Priority-Low, Type-Defect
46 | Defect | Fixed | Low |  | truongmh60003 | [TimeSheetPortlet] Java build path of project is configured not well | Priority-Low, Type-Defect
47 | Review | New | Low |  | truongmh60003 | [TimeSheetPortlet] Folder 'resouce' is placed not correctly | Priority-Low, Type-Review
48 | Defect | Fixed | Medium |  | duynd.vn | [RequirementPortlet] Use menu bar | Priority-Medium, Type-Defect
49 | Defect | Fixed | Medium |  | duynd.vn | [RequirementPortlet] Layout of screen "Add requirement" is very bad | Priority-Medium, Type-Defect
50 | Review | Fixed | Medium |  | giang.phamnguyen | [Planner] Could not click on links of projects | Priority-Medium, Type-Review
51 | Defect | Fixed | Medium |  | duynd.vn | [RequirementPortlet] User can see non-unauthorized projects | Priority-Medium, Type-Defect
52 | Defect | Fixed | Medium |  | duynd.vn | [RequirementPortlet] Could not go back the first screen | Priority-Medium, Type-Defect
53 | Defect | Fixed | Medium |  | tocongthanhhai | [ProjectEyePortlet] Could not compile source code | Priority-Medium, Type-Defect
54 | Defect | Fixed | Medium |  | duynd.vn | [RequirementPortlet] List of requirements of project is incorrect | Component-Logic, Priority-Medium, Type-Defect
55 | Defect | New | Medium |  | thachln | [ProjectEyePortlet] Click on the item with HAND CURSOR but no action | Priority-Medium, Type-Defect
56 | Defect | Fixed | Medium |  | tocongthanhhai | [ProjectEyePortlet] There is no confirmation screen before delete | Priority-Medium, Type-Defect
57 | Defect | Fixed | Medium |  | tocongthanhhai | [ProjectEyePortlet] Size of Project Code is not matched with size of field in database | Priority-Medium, Type-Defect
58 | Defect | New | Medium |  | truongmh60003 | [TimeSheetPortlet] The error occurred but no logging file | Priority-Medium, Type-Defect
59 | Defect | New | Medium |  | tocongthanhhai | [ProjectEyePortlet] Could not perform "Create New Project" in uPortal | Priority-Medium, Type-Defect
60 | Defect | New | Medium |  | tocongthanhhai | [ProjectEyePortlet] Layout of screen Create Project is not good | Component-UI, Priority-Medium, Type-Defect
61 | Defect | New | Medium |  | tocongthanhhai | [ProjectEyePortlet] Developer of the project but could not view the project | Priority-Medium, Type-Defect
62 | Defect | New | Medium |  | giang.phamnguyen | [Planner] Properties in /PlannerPortlet/resource/messages.properties are used or not? | Priority-Medium, Type-Defect
63 | Defect | New | Medium |  | giang.phamnguyen | [Planner] Non-unauthenticated projects are displayed for user | Priority-Medium, Type-Defect
64 | Defect | New | Low |  | giang.phamnguyen | [Planner] Naming Controller is not good | Priority-Low, Type-Defect
65 | Defect | New | Low |  | truongmh60003 | [RequirementPortlet] There are two resource messages | Priority-Low, Type-Defect
66 | Defect | Fixed | Low |  | duynd.vn | [RequirementPortlet] Error in JSP | Priority-Low, Type-Defect
67 | Defect | New | Medium |  | truongmh60003 | [TimeSheetPortlet] Could not compile source code | Priority-Medium, Type-Defect
68 | Defect | Fixed | Medium |  | tocongthanhhai | [ProjectEyePortlet] Paging in workOrder, Product | Priority-Medium, Type-Defect
69 | Defect | Started | Medium |  | duynd.vn | [RequirementPortlet] Portlet is displayed badly on uPortal | Priority-Medium, Type-Defect
70 | Defect | Accepted | Medium |  | duynd.vn | [RequirementPortlet] Only PM of a project can view Add button but when click add, he/she is able to add req to other project | Priority-Medium, Type-Defect
71 | Defect | New | Low |  | truongmh60003 | [TimeSheetPortlet] Duplicated libraries | Priority-Low, Type-Defect
72 | Defect | New | High |  | truongmh60003 | [TimeSheetPortlet] Error in the first screen. | Priority-High, Type-Defect
73 | Defect | New | High |  | truongmh60003 | [TimeSheetPortlet] Duplicate models with entities DaoCommon | Priority-High, Type-Defect
74 | Defect | New | Medium |  | giang.phamnguyen | [PlannerPortlet] Dialog box with unfriendly message | Priority-Medium, Type-Defect